## Sheet1
Plan of Action for Decommisioning CP4I, ODF & OCP
Phase 1 – Uninstall IBM API Connect (APIC)
S.NO | Activity
1 | Identify APIC instance
2 | Delete APIC cluster (top-level CR)
3 | Wait for all APIC pods to terminate
4 | Delete APIC backup & restore CRs
5 | Delete secret rotation CRs (mgmtsr, ptlsr)
6 | Delete Event Endpoint Management (if installed)
7 | Delete APIC-related secrets
8 | Delete Persistent Volume Claims (PVCs)
9 | Delete Crunchy PostgreSQL clusters
10 | Validate no APIC resources remain in namespace
Phase 2 – Uninstall IBM App Connect (ACE)
S.NO | Activity
1 | Delete Integration Servers
2 | Delete Integration Runtimes
3 | Delete Configurations (Policies, BAR configs, etc.)
4 | Delete App Connect Dashboard
5 | Verify no ACE pods/resources are running
Phase 3 – Uninstall Cloud Pak for Integration (CP4I)
S.NO | Activity
1 | Delete Platform Navigator
Phase 4 - Uninstall ODF (OpenShift Data Foundation)
S.NO | Activity
1 | Verify no application PVCs are using ODF storage
2 | Delete CephBlockPool(s)
3 | Delete CephFilesystem(s)
4 | Delete CephObjectStore(s) (if used)
5 | Delete StorageCluster
6 | Wait for OSD pods termination
7 | Delete ODF PVCs (if any remain)
8 | Delete ODF namespace (openshift-storage) (only if full removal)
Phase 5 – Operator Cleanup
S.NO | Activity
1 | List all IBM operator subscriptions
2 | Delete API Connect Operator subscription
3 | Delete App Connect Operator subscription
4 | Delete CP4I operators
5 | Delete ClusterServiceVersions (CSVs)
6 | Delete InstallPlans (if present)
7 | Delete CatalogSources
Phase 6 – Namespace Cleanup
S.NO | Activity
1 | Delete All Namespaces one by one
2 | Verify namespaces are removed
3 | Force delete namespace if stuck (remove finalizers)
Phase 7 – Delete OCP Cluster (Azure)
S.NO | Activity
1 | Run cluster destroy command (openshift-install destroy cluster)
2 | Monitor deletion logs
3 | Re-run destroy if partially failed
Phase 8 – Post OCP Deletion Validation (Azure)
S.NO | Activity
1 | Verify all cluster-related Resource Groups are deleted
2 | Verify all Virtual Machines (master and worker nodes) are removed
3 | Verify all Load Balancers are deleted
5 | Verify all Public IP addresses are deleted
6 | Verify DNS entries (API / Apps domains) are cleaned up
7 | Verify Service Principal (if dedicated) is removed